## ProjectSummary
ProjectName | StartDate | EndDate | Status | TotalBudget | ActualSpend | CompletedTasks | TotalTasks | CompletionPercentage
Enterprise Software Implementation | 2023-01-15 | 2023-12-15 | In Progress | 500000 | 545604.29 | 11 | 15 | 92.67

## Phases
PhaseID | Name | StartDate | EndDate | Budget
1 | Initiation | 2023-01-15 | 2023-02-28 | 50000
2 | Planning | 2023-03-01 | 2023-04-30 | 75000
3 | Execution | 2023-05-01 | 2023-10-31 | 350000
4 | Closure | 2023-11-01 | 2023-12-15 | 25000

## Milestones
MilestoneID | Name | PlannedDate | ActualDate | PhaseID
1 | Project Charter Approved | 2023-02-15 | 2023-02-18 | 1
2 | Project Plan Approved | 2023-04-15 | 2023-04-20 | 2
3 | Requirements Finalized | 2023-05-31 | 2023-06-10 | 3
4 | Development Completed | 2023-09-15 | 2023-09-30 | 3
5 | Testing Completed | 2023-10-31 | 2023-11-10 | 3
6 | Go-Live | 2023-11-30 | 2023-12-05 | 4
7 | Project Closure | 2023-12-15 |  | 4

## Tasks
TaskID | Name | PhaseID | PlannedStartDate | PlannedEndDate | ActualStartDate | ActualEndDate | Duration | Progress | ResourceID | Critical
1 | Develop Project Charter | 1 | 2023-01-15 | 2023-01-25 | 2023-01-14 | 2023-01-24 | 10 | 100 | 1 | FALSE
2 | Identify Stakeholders | 1 | 2023-01-25 | 2023-01-30 | 2023-01-26 | 2023-01-30 | 5 | 100 | 2 | TRUE
3 | Conduct Kickoff Meeting | 1 | 2023-01-30 | 2023-01-31 | 2023-01-29 | 2023-02-03 | 1 | 100 | 1 | TRUE
4 | Create Project Management Plan | 2 | 2023-03-01 | 2023-03-16 | 2023-03-03 | 2023-03-15 | 15 | 100 | 1 | TRUE
5 | Define Project Scope | 2 | 2023-03-16 | 2023-03-26 | 2023-03-15 | 2023-03-26 | 10 | 100 | 2 | TRUE
6 | Develop Schedule | 2 | 2023-03-26 | 2023-04-03 | 2023-03-24 | 2023-04-06 | 8 | 100 | 1 | TRUE
7 | Develop Budget | 2 | 2023-04-03 | 2023-04-11 | 2023-04-05 | 2023-04-11 | 8 | 100 | 1 | FALSE
8 | Gather Requirements | 3 | 2023-05-01 | 2023-05-21 | 2023-05-03 | 2023-05-20 | 20 | 100 | 2 | TRUE
9 | Create Technical Design | 3 | 2023-05-21 | 2023-06-15 | 2023-05-23 | 2023-06-16 | 25 | 100 | 3 | FALSE
10 | Develop Core Functionality | 3 | 2023-06-15 | 2023-07-15 | 2023-06-15 | 2023-07-15 | 30 | 100 | 4 | FALSE
11 | Perform Testing | 3 | 2023-07-15 | 2023-08-04 | 2023-07-14 | 2023-08-03 | 20 | 100 | 5 | FALSE
12 | Conduct User Training | 3 | 2023-08-04 | 2023-08-14 | 2023-08-03 |  | 10 | 90 | 2 | FALSE
13 | Finalize Documentation | 4 | 2023-11-01 | 2023-11-11 | 2023-11-03 |  | 10 | 80 | 2 | FALSE
14 | Conduct Post-Implementation Review | 4 | 2023-11-11 | 2023-11-16 | 2023-11-09 |  | 5 | 70 | 1 | FALSE
15 | Obtain Final Acceptance | 4 | 2023-11-16 | 2023-11-19 | 2023-11-15 |  | 3 | 50 | 1 | FALSE

## Resources
ResourceID | Name | Role | Department | Rate
1 | John Smith | Project Manager | PMO | 125
2 | Sarah Johnson | Business Analyst | Business | 95
3 | Michael Chen | Technical Lead | IT | 115
4 | Emily Davis | Developer | IT | 90
5 | Lisa Rodriguez | QA Lead | QA | 100

## ResourceAssignments
AssignmentID | TaskID | ResourceID | Role | Allocation | PlannedHours | ActualHours
1 | 1 | 1 | Project Manager | 55 | 68 | 54.4
2 | 2 | 2 | Business Analyst | 90 | 35.6 | 29.2
3 | 3 | 1 | Project Manager | 86 | 4.96 | 7.6
4 | 4 | 1 | Project Manager | 54 | 62.4 | 110.4
5 | 5 | 2 | Business Analyst | 64 | 79.2 | 54.4
6 | 6 | 1 | Project Manager | 55 | 40.96 | 35.84
7 | 7 | 1 | Project Manager | 74 | 42.88 | 50.56
8 | 8 | 2 | Business Analyst | 90 | 116.8 | 96
9 | 9 | 3 | Technical Lead | 73 | 144 | 126
10 | 10 | 4 | Developer | 92 | 160.8 | 225.6
11 | 11 | 5 | QA Lead | 93 | 145.6 | 86.4
12 | 12 | 2 | Business Analyst | 88 | 72 | 43.2
13 | 13 | 2 | Business Analyst | 84 | 76.8 | 41.6
14 | 14 | 1 | Project Manager | 60 | 31.6 | 20.72
15 | 15 | 1 | Project Manager | 67 | 21.6 | 11.28

## FinancialData
PhaseID | Month | PlannedSpend | ActualSpend | Variance | VariancePct
1 | 2023-01-01 | 35227.27 | 37851.96 | 2624.68 | 7.45
1 | 2023-02-01 | 30681.82 | 30045.49 | -636.33 | -2.07
2 | 2023-03-01 | 38750 | 42514.69 | 3764.69 | 9.72
2 | 2023-04-01 | 36250 | 44531.47 | 8281.47 | 22.85
3 | 2023-05-01 | 59289.62 | 57207.19 | -2082.43 | -3.51
3 | 2023-06-01 | 57377.05 | 55361.94 | -2015.11 | -3.51
3 | 2023-07-01 | 59289.62 | 73334.26 | 14044.64 | 23.69
3 | 2023-08-01 | 59289.62 | 66114.75 | 6825.14 | 11.51
3 | 2023-09-01 | 57377.05 | 53336.49 | -4040.56 | -7.04
3 | 2023-10-01 | 57377.05 | 62046.62 | 4669.57 | 8.14
4 | 2023-11-01 | 17045.45 | 15860.58 | -1184.87 | -6.95
4 | 2023-12-01 | 7954.55 | 7398.85 | -555.7 | -6.99

## Vendors
VendorID | Name | Type | Contact
1 | TechSolutions Inc. | Software Provider | sales@techsolutions.com
2 | Custom Cabinets Co. | Cabinet Manufacturer | info@customcabinets.com
3 | ElectroPro Services | Electrical Contractor | service@electropro.com

## Contracts
ContractID | VendorID | Description | Value | StartDate | EndDate
1 | 1 | Software License | 250000 | 2023-01-15 | 2025-01-15
2 | 2 | Custom Storage Cabinets | 35000 | 2023-06-01 | 2023-08-31
3 | 3 | Electrical Wiring Upgrade | 28000 | 2023-07-01 | 2023-09-30